## Table 1
Item | Description | Unit | Rate | Quantity | Total | Works Complete | Amount Due (HE Variation no.1) | Amount Due (HE Variation no.2 | SRA Comments | Additional Funding
1 | Works delayed until a decision is made by HE on the required VCL works | weeks | £ 5,804.05 | 4 | £23,216.20 | 100% | 23216.2 |  | Vapour barrier missed from initial design by designers - designers employed direct by 2020 House. Fire design exclusion exists in JCT contract with main contractor - is this related to fire design - not clear. | £240,614.96 additional funding provided for this work by Homes England
2 | VCL Works to Apartments | nr | £ 8,859.00 | 17 | £150,603.00 | 17 | 150603 |  | ditto | ditto
3 | Materials on site purchased for the VCL works | item | £ 5,095.50 | 1 | £5,095.50 | 1 | 5095.5 |  | ditto | ditto
4 | Additional three weeks extension due to HE decision in relation to VCL works | weeks | £ 5,804.05 | 3 | £17,412.15 | 3 | 17412.15 |  | ditto | ditto
5 | New slimsline designed scaffold to Re'new yard | Item | £23,000.00 | 1 | £23,000.00 | 1 |  | 23000 | D&B contract, scaffolding requirements contractor risk
6 | Remedial Solution to corners of building - Block 1 | item | £22,928.06 | 1 | £22,928.06 | 1 |  | 22928.06 | Steelwork missing from initial construction - does seem valid remedial works nothing to do with contractor
7 | Additional costs for the VCL works to apartment 125 & 122 being completed in isolation and out of sequence with the programmed works | nr | £ 6,174.00 | 2 | £12,348.00 | 2 |  | 12348 | VCL works | £240,614.96 additional funding provided for this work by Homes England
8 | Design, supply and installation of Non ACM Panels to isolated areas at Penthouse Level | item | £ 6,106.00 | 1 | £6,106.00 | 1 |  | 6106 | Does seem valid remedial works nothing to do with contractor
9 | Scaffolding to Phase two to be erected and hired earlier to accommodate additional lead-in time for delivery of panels. Hire to commence 25.06.2021 | weeks | £ 1,450.00 | 6 | £8,700.00 | 6 |  | 8700 | Wouldn’t expect to see this as a variation, contractor risk item?
10 | Removal of Glass curtain walling at the boundaries of the properties as requested and required by IFC and Wintech | location | £ 1,575.00 | 2 | £3,150.00 | 1 |  | 3150 | IFC fire design specifically excluded from contractor responsibilities
11 | Additional 12 weeks extension to previous programme 26.03.2021 to take account of all revised and additional fire requirements by IFC and all additional cladding requirements by Wintech | weeks | £ 5,804.05 | 12 | £69,648.60 | 12 |  | 69648.6 | IFC fire design specifically excluded from contractor responsibilities
12 | Additional 5 weeks due to delay in material shortages from Cladding manufacturer and the powder coaters | weeks | £ 5,804.05 | 5 | £29,020.25 | 5 |  | 29020.25 | Wouldn’t expect to see this as a variation, contractor risk item?
13 | Remedial Solution to corners of building - Block 2 | item | £22,928.06 | 1 | £22,928.06 | 1 |  | 22928.06 | Does seem valid remedial works nothing to do with contractor
14 | Design, supply and installation of Non ACM Panels to isolated areas at Penthouse Level as required by IFC & Wintech | item | £ 6,106.00 | 1 | £6,106.00 | 1 |  | 6106 | IFC fire design specifically excluded from contractor responsibilities
15 | Carparking - 12 spaces x £84/week x 14 weeks | item | £14,112.00 | 1 | £14,112.00 | 1 |  | 14112 | Should the requirement to displace parking have been foreseen by contractor/team who put contract together?
16 | Additional works to apartment 239 | item | £ 2,150.00 | 1 | £2,150.00 | 1 |  | 2150 | Don’t know what this is | £240,614.96 additional funding provided for this work by Homes England
17 | Replacement of broken kitchen splashes - part of VCL works | nr | £ 350.00 | 10 | £3,500.00 | 1 |  | 3500 | Same comment as VCL above | £240,614.96 additional funding provided for this work by Homes England
18 | Remove cladding panels from wall and drill additional weep holes in them - Block 1 | item | £ 5,250.00 | 1 | £5,250.00 | 1 |  | 5250 | Don’t know what this is
19 | Bathroom tiling to accommodate VCL works | item | £ 5,250.00 | 1 | £5,040.00 | 1 |  | 5040 | Same comment as VCL above | £240,614.96 additional funding provided for this work by Homes England
[6 empty] | TOTAL | 196326.85 | 233986.97
430313.82