## Sheet1
STATEMENT OF FINAL ACCOUNT
Job Reference: | 2020 House, Skinner Lane, Leeds
Issue Date: | 2022-09-20
Issued By: | Castles Special Projects LLP
Address: | 46 Broadway, Swinton, Mexborough, South Yorkshire, S64 8HF
Employer | 20:20 House (Residential Management) Limted
Address: | 20:20 House, Skinner Lane, Leeds, LS7 1BB
Contractor: | Castles Special Projects LLP
Address: | 46 Broadway, Swinton, Mexborough, South Yorkshire, S64 8HF
Works: | Cladding remedial works to 2020 House (phase 2 non-ACM Cladding)
We hereby confirm that the final account for the above works as follows:
| Contract Sum |  |  | 1504380.01
| Adjustments to the contract sum |  |  | -0.77
| [1] Provisional Sums |  | -126162.87
| [2] Variations |  | 126162.1
|  | sub total | -0.77
|  |  | Final Account (Excluding VAT) | 1504379.24
| Less: Amount certified to date |  |  | 1504379.24
| Uncertified Balance excluding Retention Currently Held (£22,565.69) |  |  | 0
Signed:
( ) for and on behalf of 2020 House (Residential Management) Ltd
………………………………………………………………………
( ) for and on behalf of Castles Special Projects LLP
………………………………………………………………………
This Statement of Final Account in the sum of £1,504,379.24 (One Million Five Hundred and Four Thousand, Three Hundred and Seventy Nine Pounds and Twenty Four Pence) + VAT is agreed for all works as full and final settlement in connection with the building contract – subject to any withholding notices the Employer may issue in respect of Liquidated and Ascertained Damages which can be properly levied under the Contract.