## Cover
SRA Project & Cost Management
2020 House (Residential Management) Limited
Interim recommendation for Payment Number 5
2022-07-01

## Valuation Cert
INTERIM RCOMMENDATION FOR PAYMENT
Issued By: |  | SRA Project & Cost Management |  |  |  | Recommendation Nr : |  | 5
Address: |  | The Leeming Building |  |  |  | Date of Issue of Recommendation: |  | 1.7.22
Ludgate Chambers
|  | Ludgate Hill |  |  |  | Reference : |  | 2020 House, Skinner Lane
|  | Leeds, LS2 7HZ | [5 empty] | Leeds
[6 empty] | Date of Application for Payment: |  | 28.6.22
Works : |  | 2020 House, Phase 2
|  |  |  | Gross Payment Recommendation |  |  |  | 991582.51
Employer |  | 2020 House (Residential Management) Limited
|  | Management Office |  | Less total amount of Retention |  | 3% |  | 29747.4753
2020 House
Skinner Lane, Leeds, LS7 1BB
Contractor : |  | Castles Special Projects LLP |  | Net Payment |  |  |  | 961835.0347
Unit 2
|  | Grange Valley Road |  | Less | Total amount previously recommended
|  | Batley |  |  | for payment to the Contractor |  |  | 683389.26
WF17 6LL
Contract Sum : |  | 1504380.01
|  |  |  | Recommended Payment |  |  |  | 278445.7747
Contract Form: |  | JCT 2016 Design and Build Contract
Notes : |  |  | We recommend the payment of
1. | All the amounts stated are exclusive of Value Added Tax. |  | Two Hundred and Seventy Eight Thousand, Four Hundred and Forty Five Pounds and Seventy Seven Pence |  |  |  | (£ | 278445.7747 | )
2. | Neither this recommendation nor subsequent certification or payment thereof is itself evidence that the design, works, materials or goods to which they relate are in accordance with this Contract.
3. | The balance stated is subject to any statutory deductions which the Employer may obliged to make under the provisions of the Construction Industry Scheme where the Employer is not classed as a 'Contractor' for the purposes of the relevant Act
Signed
4 | Payment becomes due 21 days from the date of the contractors application
|  |  | for |  | SRA Project & Cost Management Limited